## Slide 1: Project A Overview
Customer self-service portal for retail banking
Northwind Financial - Digital Channels
Notes: Welcome slide. Introduce the programme and the sponsor.

## Slide 2: Business Goals
Reduce call-centre contacts by 30 percent
Digital satisfaction score of 4.2 or higher
Launch core features within 12 months
Notes: Explain that the call-centre reduction is the main funding justification.

## Slide 3: Scope
In: balances, transactions, statements, card controls, disputes, messaging
Out: loans, investments, mobile app
Notes: Be clear that mobile is a separate programme.

## Slide 4: Technical Approach
React frontend, FastAPI backend, PostgreSQL database
Containers on Kubernetes across two availability zones
JWT authentication: HS256, 15 minute access tokens
API gateway validates every request
Notes: This is the key architecture slide. Mention that the gateway verifies tokens so services stay simple.

## Slide 5: Security
TLS 1.2 or higher in transit, AES-256 at rest
Refresh token rotation and revocation
Immutable audit log retained seven years
Notes: Compliance reviewers care most about the audit log.

## Slide 6: Team and Delivery
6 engineers, 1 designer, 1 product owner
Two-week sprints, staging release every sprint
Monthly usability sessions with customers
Notes: Mention the team is split across two sites.

## Slide 7: Results So Far
Load test: 5000 concurrent users, 1.4 s p95 latency
Active users grew from 800 in January to 4890 in December
Annual revenue contribution 655000 USD
Notes: Numbers come from Project_Metrics.xlsx.

## Slide 8: Timeline
Design complete: Q1
Beta with staff: Q3
Public launch: Q4
Notes: Launch depends on the security audit sign-off.

## Slide 9: Delivery Milestones
Milestone | Planned | Actual | Status
Design complete | Mar | Mar | Done
Beta with staff | Sep | Oct | Done
Security audit | Oct | Nov | Done
Public launch | Dec | - | Planned
Notes: Beta slipped one month because the security audit was rescheduled.

## Slide 10: Revenue by Quarter (native chart)
Chart: 
| Q1 | Q2 | Q3 | Q4
Revenue_USD | 120000 | 150000 | 175000 | 210000

## Slide 11: Deployment View
Notes: Walk through the request path left to right.

## Slide 12: Revenue Chart (picture)